## Roadmap
Product Roadmap Template
Edit the white cells. Gates come from the Program block; every task shows the gate it delivers to and its due date.
PROGRAM START |  | 2027-01-01
DISCIPLINE | CODE | ITEM | TYPE | START | END | DELIVERS TO | DUE | 2027 | [11 empty] | 2028 | [11 empty] | 2029
[8 empty] | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
[8 empty] | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01 | 2028-01-01 | 2028-02-01 | 2028-03-01 | 2028-04-01 | 2028-05-01 | 2028-06-01 | 2028-07-01 | 2028-08-01 | 2028-09-01 | 2028-10-01 | 2028-11-01 | 2028-12-01 | 2029-01-01 | 2029-02-01 | 2029-03-01 | 2029-04-01 | 2029-05-01 | 2029-06-01 | 2029-07-01 | 2029-08-01 | 2029-09-01 | 2029-10-01 | 2029-11-01 | 2029-12-01
Program | Owner |  | Goal
|  | Concept | Phase | 2027-01-01 | 2027-07-10
|  | Development | Phase | 2027-08-01 | 2028-04-10
|  | Validation | Phase | 2028-04-16 | 2028-12-10
|  | Launch | Phase | 2029-01-01 | 2029-06-10
|  | Series | Phase | 2029-07-01 | 2029-12-31
|  | A-sample | Milestone | 2027-11-15 | bar: 2027-11-01
|  | B-sample | Milestone | 2028-08-15 | bar: 2028-08-01
| G1 | Concept freeze | Gate | 2027-07-31 | bar: 2027-07-01
| G2 | Design freeze | Gate | 2028-04-15 | bar: 2028-04-01
| G3 | Production release | Gate | 2028-12-31 | bar: 2028-12-01
| G4 | SOP | Gate | 2029-06-30 | bar: 2029-06-01
Mechanics | Owner |  | Goal
|  | Thermal concept | Task | 2027-01-01 | 2027-07-10 | G1 | 2027-07-31 | bar: 2027-07-01
|  | Housing & gearbox | Task | 2027-08-01 | 2028-04-10 | G2 | 2028-04-15 | bar: 2028-04-01
|  | Tooling | Task | 2028-04-16 | 2028-12-10 | G3 | 2028-12-31 | bar: 2028-12-01
|  | Durability testing | Task | 2028-04-16 | 2028-12-10 | G3 | 2028-12-31 | bar: 2028-12-01
E/E & software | Owner |  | Goal
|  | E/E architecture | Task | 2027-01-01 | 2027-07-10 | G1 | 2027-07-31 | bar: 2027-07-01
|  | Inverter hardware | Task | 2027-08-01 | 2028-04-10 | G2 | 2028-04-15 | bar: 2028-04-01
|  | EMC & safety | Task | 2028-04-16 | 2028-12-10 | G3 | 2028-12-31 | bar: 2028-12-01
|  | Software releases | Task | 2027-08-01 | 2029-06-10 | G4 | 2029-06-30 | bar: 2029-06-01
Manufacturing | Owner |  | Goal
|  | Plant concept | Task | 2027-01-01 | 2027-07-10 | G1 | 2027-07-31 | bar: 2027-07-01
|  | Supplier selection | Task | 2027-08-01 | 2028-04-10 | G2 | 2028-04-15 | bar: 2028-04-01
|  | Line installation | Task | 2028-04-16 | 2028-12-10 | G3 | 2028-12-31 | bar: 2028-12-01
|  | Process validation | Task | 2028-04-16 | 2028-12-10 | G3 | 2028-12-31 | bar: 2028-12-01
|  | Ramp-up | Task | 2029-01-01 | 2029-06-10 | G4 | 2029-06-30 | bar: 2029-06-01
[14 empty] | G1 | [8 empty] | G2 | [7 empty] | G3 | [5 empty] | G4
Note on D4: Input: first month of the program. Years and months follow this date.

## How to use
How to use this product roadmap
01 | Set the program start | Enter the first month of the program in cell D4 on the Roadmap sheet. Years and months follow it.
02 | Define the program gates | Add one Gate row per gate in the Program block, with code (G1, G2 …) and date. Pink lines and labels follow the dates.
03 | Link every task to a gate | In each discipline, choose the gate a task delivers to. Due date and delivery dot move with the gate.
04 | Read each gate line top to bottom | A gate decision needs every delivery marked on its line, from every discipline.
05 | Decide at every gate | Close each gate with a decision: release, rework or stop.
Types
| Phase | Program phase between two gates
| Task | Discipline work; the bar takes the tone of its discipline
● | Milestone | Fixed date, such as a sample build
◆ | Gate | Program decision; draws the pink line all disciplines deliver to
● | Delivery | Shown in a task row at the gate it delivers to
Pharma and defense teams can rename the disciplines, for example to CMC, Clinical and Regulatory, or to subsystems and integration.
Need more rows? Copy an existing row inside a block and insert it as copied cells, so the timeline formulas come along.