## Roadmap
Project Roadmap Template
Edit the white cells. Bars, gate lines and gate labels follow Type, Start and End.
PROJECT START |  | 2027-01-01
PHASE | CODE | TASK | TYPE | START | END | Q1 | [12 empty] | Q2 | [12 empty] | Q3 | [12 empty] | Q4
[6 empty] | Jan |  |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  |  | Aug |  |  |  | Sep |  |  |  | Oct |  |  |  |  | Nov |  |  |  | Dec
 | time axis 2027-01-01 to 2027-12-24
1 Research | Owner |  | Goal
| 1.1 | Stakeholder interviews | Task | 2027-01-04 | 2027-02-12
| 1.2 | Process audit | Task | 2027-02-01 | 2027-03-24
| G1 | Business case | Gate | 2027-03-26 | bar: 2027-03-26
2 Concept | Owner |  | Goal
| 2.1 | Solution design | Task | 2027-03-29 | 2027-05-03
| 2.2 | Vendor selection | Task | 2027-04-19 | 2027-05-26
| G2 | Project plan | Gate | 2027-05-28 | bar: 2027-05-28
3 Prototype | Owner |  | Goal
| 3.1 | Sensor retrofit, line 1 | Task | 2027-06-01 | 2027-07-20
| 3.2 | Predictive model | Task | 2027-07-06 | 2027-09-22
| 3.3 | Roll out line 1 first | Decision | 2027-09-24 | bar: 2027-09-24
| G3 | Pilot report | Gate | 2027-09-24 | bar: 2027-09-24
4 Roll out | Owner |  | Goal
| 4.1 | Operator training | Task | 2027-09-28 | 2027-11-03
| 4.2 | Go-live, line 1 | Task | 2027-10-19 | 2027-11-30
| G4 | Handover | Gate | 2027-12-02 | bar: 2027-11-26
[18 empty] | G1 | [8 empty] | G2 | [16 empty] | G3 | [8 empty] | G4
Note on D4: Input: first day of the project timeline. Weeks, months and quarters follow this date.

## How to use
How to use this project roadmap
01 | Set the project start | Enter the first day of the timeline in cell D4 on the Roadmap sheet. Weeks, months and quarters follow it.
02 | Name owner and goal per phase | Assign one owner per phase and state the goal the phase must reach before its gate.
03 | Add one row per task | Enter code, task, type, start and end. Milestones, decisions and gates need a start date only.
04 | End every phase in a gate | Add one Gate row per phase with the deliverable the gate reviews. The pink line and label move with its date.
05 | Decide at every gate | Close each gate with a decision: continue, change scope or stop the project.
Types
| Task | Work with a start and end date; the bar takes the tone of its phase
● | Milestone | Fixed date inside a phase
◆ | Decision | Choice the plan depends on
● | Gate | Phase end with its deliverable; draws the pink gate line and label
Need more rows? Copy an existing row inside a phase and insert it as copied cells, so the timeline formulas and phase tone come along.