## Technology Roadmap
Technology Roadmap Template
Edit the white cells. The timeline fills itself from Type, Start and End.
FIRST YEAR |  | 2027
LAYER | CODE | ITEM | TYPE | START | END | DEPENDS ON | 2027 |  |  |  | 2028 |  |  |  | 2029 |  |  |  | 2030 |  |  |  | 2031
[7 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
[7 empty] | 2027-01-01 | 2027-04-01 | 2027-07-01 | 2027-10-01 | 2028-01-01 | 2028-04-01 | 2028-07-01 | 2028-10-01 | 2029-01-01 | 2029-04-01 | 2029-07-01 | 2029-10-01 | 2030-01-01 | 2030-04-01 | 2030-07-01 | 2030-10-01 | 2031-01-01 | 2031-04-01 | 2031-07-01 | 2031-10-01
Market drivers | Owner
| M1 | Customers expect 15-min charging | Market driver | 2027-05-15 | bar: 2027-04-01
| M2 | Rare-earth supply squeeze | Market driver | 2028-05-15 | bar: 2028-04-01
| M3 | 800V goes mainstream | Market driver | 2029-08-15 | bar: 2029-07-01
| M4 | EU fleet CO2 −55% | Market driver | 2030-01-01 | bar: 2030-01-01
Products | Owner
| P1 | Gen 2 e-drive | Product | 2027-01-01 | 2028-08-07
| P1 | Start of production | Milestone | 2027-11-15 | bar: 2027-10-01
| P2 | Gen 3 800V e-drive | Product | 2029-02-24 | 2031-12-31 | C1
| P3 | Rare-earth-free e-axle | Product | 2030-03-15 | 2031-12-31 | C3
Components | Owner
| C1 | SiC inverter | Component | 2027-11-24 | 2029-05-27 | T1
| C2 | Hairpin stator | Component | 2027-01-01 | 2027-12-14
| C3 | Magnet-free rotor | Component | 2029-02-06 | 2030-04-20 | T2
| C4 | Integrated thermal module | Component | 2030-06-14 | 2031-12-31
Technologies | Owner
| T1 | SiC semiconductors | Technology | 2027-01-01 | 2028-03-14
| T2 | Magnet-free motor design | Technology | 2027-01-01 | 2028-12-06
| T2 | Scale to series | Decision | 2028-12-31 | bar: 2028-10-01
| T3 | AI-based motor control | Technology | 2029-08-07 | 2031-12-31
[10 empty] | 2027 review |  |  |  | 2028 review |  |  |  | 2029 review |  |  |  | 2030 review |  |  |  | 2031 review
Note on D4: Input: first year of the roadmap. Years, quarters and review lines follow it.

## Product Roadmap
Product Roadmap Template
Edit the white cells. Gates come from the Program block; every task shows the gate it delivers to and its due date.
PROGRAM START |  | 2027-01-01
DISCIPLINE | CODE | ITEM | TYPE | START | END | DELIVERS TO | DUE | 2027 | [11 empty] | 2028 | [11 empty] | 2029
[8 empty] | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
[8 empty] | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01 | 2028-01-01 | 2028-02-01 | 2028-03-01 | 2028-04-01 | 2028-05-01 | 2028-06-01 | 2028-07-01 | 2028-08-01 | 2028-09-01 | 2028-10-01 | 2028-11-01 | 2028-12-01 | 2029-01-01 | 2029-02-01 | 2029-03-01 | 2029-04-01 | 2029-05-01 | 2029-06-01 | 2029-07-01 | 2029-08-01 | 2029-09-01 | 2029-10-01 | 2029-11-01 | 2029-12-01
Program | Owner |  | Goal
|  | Concept | Phase | 2027-01-01 | 2027-07-10
|  | Development | Phase | 2027-08-01 | 2028-04-10
|  | Validation | Phase | 2028-04-16 | 2028-12-10
|  | Launch | Phase | 2029-01-01 | 2029-06-10
|  | Series | Phase | 2029-07-01 | 2029-12-31
|  | A-sample | Milestone | 2027-11-15 | bar: 2027-11-01
|  | B-sample | Milestone | 2028-08-15 | bar: 2028-08-01
| G1 | Concept freeze | Gate | 2027-07-31 | bar: 2027-07-01
| G2 | Design freeze | Gate | 2028-04-15 | bar: 2028-04-01
| G3 | Production release | Gate | 2028-12-31 | bar: 2028-12-01
| G4 | SOP | Gate | 2029-06-30 | bar: 2029-06-01
Mechanics | Owner |  | Goal
|  | Thermal concept | Task | 2027-01-01 | 2027-07-10 | G1 | 2027-07-31 | bar: 2027-07-01
|  | Housing & gearbox | Task | 2027-08-01 | 2028-04-10 | G2 | 2028-04-15 | bar: 2028-04-01
|  | Tooling | Task | 2028-04-16 | 2028-12-10 | G3 | 2028-12-31 | bar: 2028-12-01
|  | Durability testing | Task | 2028-04-16 | 2028-12-10 | G3 | 2028-12-31 | bar: 2028-12-01
E/E & software | Owner |  | Goal
|  | E/E architecture | Task | 2027-01-01 | 2027-07-10 | G1 | 2027-07-31 | bar: 2027-07-01
|  | Inverter hardware | Task | 2027-08-01 | 2028-04-10 | G2 | 2028-04-15 | bar: 2028-04-01
|  | EMC & safety | Task | 2028-04-16 | 2028-12-10 | G3 | 2028-12-31 | bar: 2028-12-01
|  | Software releases | Task | 2027-08-01 | 2029-06-10 | G4 | 2029-06-30 | bar: 2029-06-01
Manufacturing | Owner |  | Goal
|  | Plant concept | Task | 2027-01-01 | 2027-07-10 | G1 | 2027-07-31 | bar: 2027-07-01
|  | Supplier selection | Task | 2027-08-01 | 2028-04-10 | G2 | 2028-04-15 | bar: 2028-04-01
|  | Line installation | Task | 2028-04-16 | 2028-12-10 | G3 | 2028-12-31 | bar: 2028-12-01
|  | Process validation | Task | 2028-04-16 | 2028-12-10 | G3 | 2028-12-31 | bar: 2028-12-01
|  | Ramp-up | Task | 2029-01-01 | 2029-06-10 | G4 | 2029-06-30 | bar: 2029-06-01
[14 empty] | G1 | [8 empty] | G2 | [7 empty] | G3 | [5 empty] | G4
Note on D4: Input: first month of the program. Years and months follow this date.

## Strategy Roadmap
Strategy Roadmap Template
Edit the white cells. The timeline fills itself from Type, Start and End.
ROADMAP START |  | 2027-01-01
LEVEL | CODE | ITEM | TYPE | START | END | Q1 | [12 empty] | Q2 | [12 empty] | Q3 | [12 empty] | Q4
[6 empty] | Jan |  |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  |  | Aug |  |  |  | Sep |  |  |  | Oct |  |  |  |  | Nov |  |  |  | Dec
 | time axis 2027-01-01 to 2027-12-24
Company | Owner |  | Goal
| O1 | Grow new-product revenue to 25% of sales | Objective | 2027-01-01 | 2027-09-30
| O2 | Cut product CO2 footprint by 40% | Objective | 2027-04-01 | 2027-12-31
Department | Owner |  | Goal
| 1.1 | Tech scouting | Initiative | 2027-01-18 | 2027-03-25
| 1.1 | Partner route chosen | Decision | 2027-04-01 | bar: 2027-03-26
| 1.2 | Partner pilot | Initiative | 2027-04-08 | 2027-07-20
| 2.1 | Recycled materials | Initiative | 2027-07-27 | 2027-10-20
| 2.2 | Low-carbon suppliers | Initiative | 2027-08-17 | 2027-11-30
Group | Owner |  | Goal
| 1.1.1 | Scoping | Project | 2027-02-06 | 2027-03-31
| 1.2.1 | Development | Project | 2027-04-03 | 2027-09-15
| 1.2.1 | Prototype | Milestone | 2027-05-20 | bar: 2027-05-14
| 1.2.1 | Field test | Milestone | 2027-08-10 | bar: 2027-08-06
| 1.2.2 | Tests | Project | 2027-09-18 | 2027-11-03
| 1.2.3 | Scale-up | Project | 2027-11-06 | 2027-12-31
| 1.2.3 | Launch | Milestone | 2027-12-20 | bar: 2027-12-17
Team | Owner |  | Goal
| 1.1 | 5 partners screened | KPI | 2027-03-31 | bar: 2027-03-26
| 1.2.1 | 95% test pass rate | KPI | 2027-06-30 | bar: 2027-06-25
| 2.1 | 30% recycled content | KPI | 2027-09-30 | bar: 2027-09-24
| 1.2.3 | 1,000 units shipped | KPI | 2027-12-31 | bar: 2027-12-24
[16 empty] | Q1 review | [12 empty] | Q2 review | [12 empty] | Q3 review | [12 empty] | Q4 review
Note on D4: Input: first day of the roadmap year. Week columns, months and quarters follow this date.

## Project Roadmap
Project Roadmap Template
Edit the white cells. Bars, gate lines and gate labels follow Type, Start and End.
PROJECT START |  | 2027-01-01
PHASE | CODE | TASK | TYPE | START | END | Q1 | [12 empty] | Q2 | [12 empty] | Q3 | [12 empty] | Q4
[6 empty] | Jan |  |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  |  | Aug |  |  |  | Sep |  |  |  | Oct |  |  |  |  | Nov |  |  |  | Dec
 | time axis 2027-01-01 to 2027-12-24
1 Research | Owner |  | Goal
| 1.1 | Stakeholder interviews | Task | 2027-01-04 | 2027-02-12
| 1.2 | Process audit | Task | 2027-02-01 | 2027-03-24
| G1 | Business case | Gate | 2027-03-26 | bar: 2027-03-26
2 Concept | Owner |  | Goal
| 2.1 | Solution design | Task | 2027-03-29 | 2027-05-03
| 2.2 | Vendor selection | Task | 2027-04-19 | 2027-05-26
| G2 | Project plan | Gate | 2027-05-28 | bar: 2027-05-28
3 Prototype | Owner |  | Goal
| 3.1 | Sensor retrofit, line 1 | Task | 2027-06-01 | 2027-07-20
| 3.2 | Predictive model | Task | 2027-07-06 | 2027-09-22
| 3.3 | Roll out line 1 first | Decision | 2027-09-24 | bar: 2027-09-24
| G3 | Pilot report | Gate | 2027-09-24 | bar: 2027-09-24
4 Roll out | Owner |  | Goal
| 4.1 | Operator training | Task | 2027-09-28 | 2027-11-03
| 4.2 | Go-live, line 1 | Task | 2027-10-19 | 2027-11-30
| G4 | Handover | Gate | 2027-12-02 | bar: 2027-11-26
[18 empty] | G1 | [8 empty] | G2 | [16 empty] | G3 | [8 empty] | G4
Note on D4: Input: first day of the project timeline. Weeks, months and quarters follow this date.